## Schedule
Capstone Project Schedule Template - Fall-Spring
Project:
|  |  | Last Updated: | 2020-10-06
|  |  | Year | 2020 | [16 empty] | 2021
|  |  | Month | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May
| Task Description | Duration | Assigned | 2020-09-05 | 2020-09-12 | 2020-09-19 | 2020-09-26 | 2020-10-03 | 2020-10-10 | 2020-10-17 | 2020-10-24 | 2020-10-31 | 2020-11-07 | 2020-11-14 | 2020-11-21 | 2020-11-28 | 2020-12-05 | 2020-12-12 | 2020-12-19 | 2020-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 | 2021-01-30 | 2021-02-06 | 2021-02-13 | 2021-02-20 | 2021-02-27 | 2021-03-06 | 2021-03-13 | 2021-03-20 | 2021-03-27 | 2021-04-03 | 2021-04-10 | 2021-04-17 | 2021-04-24 | 2021-05-01 | 2021-05-08 | 2021-05-15 | 2021-05-22 | 2021-05-29
| Load, Generator, Wire, and Bus blocks | 8 | Christian
| PandaPower Socket Interface | 5 | Zach
| Block and Item Components | 8 | Christian
| PandaPower Server integration | 4 | Zach
| Chat interface | 1 | Zach
| Measurements and GUI | 5 | Zach
| Asset Models | 2 | Christian
| Transformer, Switches, and Storage | 6 | Christian
| 3 phase power | 5 | Zach
| Custom blocks (i.e. Electric Furnace) | 6 | Zach
| Redstone Integration | 7 | Christian
| Custom Configurations | 2 | Zach
| Power network creation | 8 | Zach
| Testing | 1 | Zach
| Testing | 4 | Christian
| Documentation/Wiki | 4 | Christian